###### King Edward VI School, Lichfield							ICT Development Plan 2001

| Development areas | Approaches | Success Criteria | Staff development | Resources & Costs | Timescale |
| --- | --- | --- | --- | --- | --- |
| Use of ICT as a powerful learning tool Integrate ICT curriculum and subject curriculum ICT modules need to address National Curriculum 2000 | Encourage, advise & support more departments to build in use of IT to schemes of work Revise ICT modules to make better contribution to subject/curriculum Training for Science, Business; English, Geography; History, RE, PE departments Provide interactive whiteboards in classrooms and labs | ICT being used in the majority of lessons ICT modules an integral part of subject curriculum at Key Stage 3 Subject schemes of work and ICT modules timed to complement each other | New Opportunities Fund training Training for staff in their use | Costs of training met by NOF. Supply cover to be met from TSF (1½ days @ £180 per member of staff) 4 @ £7000 (from NGfL) | 60% of staff will have completed NOF training by December 2001 New modules in place for MFL, Geography Maths by September 2001; Science and English by January 2002 Summer term 2001 September 2001 |

| Development areas | Approaches | Success Criteria | Staff development | Resources & Costs | Timescale |
| --- | --- | --- | --- | --- | --- |
| Provide students with more opportunities to develop as autonomous users of ICT | Revise ICT modules and schemes of work to emphasise independent learning and the development of transferable ICT skills for future use. Increase open access facilities Provide access to school network from home | ICT embedded in schemes of work as a tool for students to use when they see the need. Students able to work on-line from home | New Opportunities Fund training | Costs of training met by NOF. Supply cover to be met from TSF (1½ days @ £180 per member of staff) Increase provision of computers in all classrooms (see below) £320 per annum | New modules in place for MFL, Geography Maths by September 2001; Science and English by January 2002 New modules from other subjects on a rolling programme September 2001 |

| Development areas | Approaches | Success Criteria | Staff development | Resources & Costs | Timescale |
| --- | --- | --- | --- | --- | --- |
| Enable students to attain Level 7 or above at Key Stage 3 | Review assessment procedures Refine IT modules and assessment to allow more differentiation and access to NC Levels 7/8. Bring more departments into the assessment regime Support development of additional modules | An increase in numbers of students achieving Level 7+ at Key Stage 3 in ICT by July 2002 Assessments from additional modules fed into student attainment calculations | New Opportunities Fund training | Costs of training met by NOF. Supply cover to be met from TSF (1½ days @ £180 per member of staff) | New assessment opportunities in place by September 2001 New modules in place for MFL, Geography Maths by September 2001; Science and English by January 2002 New modules from other subjects on a rolling programme |
| Develop Measurement & Control strands | Science & Geography departments to develop new Measurement modules | Revised modules in place | InSeT time for members of department to work together to develop module | Supply Cover (£500 for up to 4 members of department for one day) Hardware costs met from NGfL (see below) | September 2001 |
| Ensure coverage of ICT National Curriculum at Key Stage 4 | Map subject schemes of work to ICT NC at KS4 and Key Skill level 2 ICT courses at KS4 rectify any deficit | ICT National Curriculum at KS4 covered Students reach Key Skill Level 2 by end of Year 11 | Staff development time for mapping exercise | Supply costs at £150 per day | September 2002 |

| Development areas | Approaches | Success Criteria | Staff development | Resources & Costs | Timescale |
| --- | --- | --- | --- | --- | --- |
| Provide increased opportunities for accreditation in ICT post-16 | Provide teaching to Key Skill Level 3 for all Year 12 students alongside IBT Introduce ICT Advanced VCE | Most of Year 12 students to have improved their ICT Key Skill Level by at least one level | Course development time | Supply Cover (£500 for 3 staff for two days) Rooming & timetable implications | July 2001 September 2001 |
| Improve teacher competence and confidence in use of ICT | Continue to provide basic ICT skills training for those who need it Integration of skills training with NOF training | Evaluation of training shows that teachers are more confident and competent in the use of ICT and are making more use of it in their teaching CLAIT accreditation gained by some teachers | Basic skills training in twilight sessions | Trainer time and materials | Continuation of modules in Summer term 2001 New programme from September 2001 |

| Development areas | Approaches | Success Criteria | Staff development | Resources & Costs | Timescale |
| --- | --- | --- | --- | --- | --- |
| Improve access to up-to-date ICT facilities | Continue programme of updating hardware Provide networked computers to all classrooms Conversion to broadband Internet connection | Pupil:Computer ratio of 1:7 All computers networked, and access to network from every classroom Clusters created at strategic points around school |  | Provision of an additional 43 networked computers to all main building classrooms; two more file servers; one additional multimedia server (NGfL funding £70000 in 2001/2) Access to computers in mobiles £1800 in 2001/2 £3000 in 2002/3 £6000 in 2003/4 £10000 in 2004/5 | September 2001 September 2002 Spring 2002 |
| Make available state of the art CAD/CAM and Control ICT facilities | Update hardware in CDT block | Cluster of hardware in place |  | NGfL funding | September 2001 |
| Enable teachers to utilise the power of ICT for administration tasks | Link curriculum and administration networks Training of teachers | Teachers have access to student data | Training in SIMS for staff (twilight sessions) |  | January 2002 July 2003 |
| Promote community use of ICT facilities | Work with Youth & Community Education Service to provide evening CLAIT, IBT classes | One class per week offered |  | Use of room 22 | from April 2001 |